Spring Research Project: Mentor Rubric

Mentor Name(s): Nihar Dalal

Mentee Name(s):

Project Title: Cosmology with Type Ia Supernovae

In a short paragraph, explain the project and its learning objectives:

Using data from the 1998 Supernova Cosmology Project, https://supernova.lbl.gov/Union/, we plan to calculate the Hubble constant! We also want to try fitting more complicated models of cosmology (eg. Omega_lambda) and see what parameters we might be able to constrain from the data.

The learning objectives are:

- Become more familiar with python and data analysis

- Learn how to fit data to models, especially with error bars.

- Become more familiar with basic cosmological models (lambda CDM)

- Learn about type Ia Supernovae as standard candles

What are the deliverables? (i.e. plot/figure/image/equation mentee will reach)

Deliverables include a Hubble plot (distance modulus vs redshift) populated with several supernovae, and fits with several models, as well as a derived value of the Hubble constant with an estimate on the error, and perhaps the same for the equation of state parameter.

Project Calendar: Indicate what the mentee will be expected to do each week. Work days are indicated in the left column. Include estimated time, resources, in/out of class work, and whether it is completed on their own or with you. The project should take 8-10 hours in total.

| Dates: | Tasks: |
| --- | --- |
| Week 1 (2/12) Intro to Project | Introduce the project, install necessary software, and download data. |
| Week 2 (2/19) Outside of Class Work | Read some simple articles about the standard candle/distance ladder method of calculating H0. |
| Week 3 (2/26) In class work day | Read the data using pandas, and plot it. |
| Week 4 (3/4) Outside of Class Work | Read up on cosmology models, namely how dark energy implies an expanding universe, and what that would look like for our Hubble plot. |
| Spring Break | None |
| Week 5 (3/18) | Start fitting models. Start with the linear model using scipy, and calculate H0. |
| Week 6 (3/25) In Class Work Day | Implement a more complex model with additional parameters (Omega_M and Omega_Lambda) |
| Week 7 (4/1) In Class Work Day | Mess around with some more complex stuff – other models, covariance matrix? |
| Week 8 (4/8) Poster Work Day | Work on Poster! |
| Week 9 (4/15) Present! |  |

Reading List: (Make sure material is level appropriate.)

https://supernova.lbl.gov/

https://www.science.org/doi/10.1126/science.302.5653.2038

https://www.slac.stanford.edu/econf/C990809/docs/perlmutter.pdf

https://www.aps.org/publications/apsnews/200901/physicshistory.cfm

https://www.pbs.org/wgbh/nova/universe/

https://www.scientificamerican.com/article/dark-forces-at-work/

https://www.scientificamerican.com/article/expanding-universe-slows-then-speeds/#:~:text=The%20most%20plausible%20explanation%20for,speeding%20up%2C%20not%20slowing%20down.

https://www.scientificamerican.com/article/a-cosmic-conundrum-2006-01/
https://en.wikipedia.org/wiki/Cosmic_distance_ladder

https://www.astronomy.com/science/the-cosmic-distance-ladder-how-we-measure-an-infinite-universe/

https://people.ast.cam.ac.uk/~pettini/Intro%20Cosmology/Lecture17.pdf

Official Article: https://iopscience.iop.org/article/10.1238/Physica.Topical.085a00047/pdf

Resource List:  (This should include lab space, instruments, and software. Note that mentees are not allowed to complete research projects that require safety training operation of lab equipment. If you feel this is detrimental to your project, please petition Polaris leadership.)

Anaconda, Jupyter, Pandas, https://supernova.lbl.gov/

Other Notes:

This might be a little easy, but I think we can make the project more complicated as we go along.